## README
Config based generic ETL framework
ASPECT ORDER
1. Load type model | CLOSED (pending OQ-01)
2. Configuration data model | in progress
3. Target table types and write strategies | NEXT
4. Window derivation mechanics
5. Execution engine skeleton, gates, phase sequence
6. DQ and reconciliation from config
7. Orchestration, DAG declaration and grouping
8. State, restart and observability
9. Governance and lifecycle

## load_type and window strategy
Load types
Load type | Window strategy | Default pass mode | Cleanup required first | What it is for
HISTORY | EXPLICIT_RANGE | CHUNKED | No | Bulk backfill over a wide range. Target is empty.
CATCHUP | EXPLICIT_RANGE | SINGLE | No | The gap between the end of history and the first incremental. Same execution pattern as HISTORY
INCREMENTAL | DERIVED_WATERMARK | SINGLE | No | The routine run. Frequency (daily / weekly / monthly) lives on the schedule, not here.
REPLAY | EXPLICIT_RANGE | SINGLE | Yes | Reload of a corrected range over data the target already holds. The cleanup precondition is what makes it a distinct type.
FULL_REFRESH | ALL_ROWS | SINGLE | Yes (implicit) | The 'static table' case. ALSO the fallback for any table whose source has no reliable watermark or CDC column.
SNAPSHOT_APPEND | ALL_ROWS | SINGLE | No | Retain every point-in-time snapshot rather than overwriting. | yet to discuss and confirm
Window strategies
Window strategy | How the window is derived | What it outputs | Notes
DERIVED_WATERMARK | From the stored high-water mark for this pipeline | A bounded range: last successful mark to the current upstream end | Seeding a new pipeline is an insert; this removes the need for a 'first-time incremental' load type entirely.
EXPLICIT_RANGE | From a supplied start and end | The supplied range, optionally cut into chunks | Serves HISTORY, CATCHUP and REPLAY. The three differ only in where the dates come from and whether cleanup is required first.
ALL_ROWS | No filter | Every row in the source | Serves FULL_REFRESH and SNAPSHOT_APPEND. Chunking still applies when volume demands it.

## table_type
Target table types
Target table type | Invariant it must preserve | Example tables | Teams using it | Approx. share of tables
SCD1 | Exactly one row per business key, holding the latest source state. |  |  |  | need to fill details
SCD2 | Per business key, the rows form a contiguous, non-overlapping cover of time from first-seen to high date, with exactly one row carrying the current marker. |  |  |  | need to fill details
APPEND_ONLY | Every source event appears exactly once; no existing row is ever modified or deleted. Identity is the event, not the entity. |  |  |  | yet to discuss and confirm
SNAPSHOT | For every snapshot period, the complete population as at that period; a period is immutable once written. |  |  |  | need to fill details
Table-level properties that constrain write strategy
Property | What it means | Why it constrains the write strategy
has_referenced_surrogate_key | Another table holds a foreign key to this table's generated surrogate key | TRUNCATE_INSERT re-mints surrogate keys every run and breaks every FK pointing at them
is_ri_parent | Child tables resolve their foreign keys against this table | TRUNCATE_INSERT leaves the table briefly EMPTY; a concurrent child load orphans every row
keeps_audit_lineage | 'When did this row first appear' must survive across runs | TRUNCATE_INSERT resets audit_create_datetime on every row, so first-seen is lost

## write_strategy
Write strategies — TO BE FILLED (Aspect 3)
Write strategy | Serves table types | Idempotent? | Requires from the window | Cleanup needed on replay? | Notes | Status
MERGE_SCD1 | SCD1 | Yes | The delta rows only | No | Plain upsert on the business key | EXAMPLE ROW — delete

## compatibility
Table type x write strategy compatibility
Target table type | Write strategy | Valid? | Reason if invalid or unsafe | delete this worksheet if nothing new needs to be added
SCD2 | TRUNCATE_INSERT | NO | Destroys the cover of time before this run's window. Violates SCD2 assertion (2), no gap. Expressible and does not error, which is what makes it dangerous - it must be blocked at validation.
SCD2 | MERGE_SCD1 | NO | Collapses the timeline to one row per key. Violates SCD2 assertions (1) and (2).
APPEND_ONLY | any strategy with an UPDATE path | NO | Violates the invariant directly: no existing row is ever modified.
SCD1 | TRUNCATE_INSERT | CONDITIONAL | Valid only under the derivable rule on the table_type sheet: window = ALL_ROWS and the table is neither surrogate-key-referenced nor an RI parent. This is the 'static / config / mapping table' case.
SCD1 | MERGE_SCD1 | YES | Preserves the invariant, the surrogate keys and the audit lineage. The default for an SCD1-shaped dimension.

## pipeline_inventory
Pipeline inventory — TO BE FILLED BY THE TEAMS
The demand side. Answers OQ-05, OQ-06, OQ-07 and OQ-10, which gate the write-strategy set. Pick tables at the extremes first: most source tables, deepest dependency, largest volume, oddest target shape. 3-5 per team is enough. The last three columns decide whether TRUNCATE_INSERT is legal for that table.
Team | Source system | Target database | Target schema | Target table | Target table type | No. of source tables | Multi-source AND both keep history? | Delete detection required? | Load types needed | Approx. row count | Parent tables (load before this) | Notes | Surrogate key referenced by other tables? | Is RI parent? | Audit lineage must be preserved?
Broker | CMPM | ZONE2_DB | BROKER_DD | Z2_BROKER_PARTY_ADDRESS | SCD2 | 2 | Yes | No | HISTORY, CATCHUP, INCREMENTAL | 12,000,000 | Z2_BROKER_PARTY_DIM | EXAMPLE ROW — delete | Yes | Yes | Yes

## decisions
Decisions log
ID | Decision | Status | Aspect / category
D-01 | Nine load types are modelled as three orthogonal axes plus named presets, not nine entities | CLOSED | Aspect 1
D-02 | 'Truncate and load' is a write strategy, not a load type | CLOSED | Aspect 1
D-03 | Frequency lives on the schedule, not in the load model. One INCREMENTAL | CLOSED | Aspect 1
D-04 | 'Static table load' becomes FULL_REFRESH, reusable beyond static tables | CLOSED | Aspect 1
D-05 | Chunking is an attribute of any load, available to every window strategy | CLOSED | Aspect 1
D-06 | File-based sources are out of scope. Re-entry cost: a fourth window strategy, a file registry, format validation ahead of row-level DQ, trailer / control-total reconciliation | CLOSED | Scope
D-07 | HISTORY and CATCHUP share one execution pattern but keep two names, for audit and governance | CLOSED | Aspect 1
D-08 | REPLAY is a distinct named load type, because of its cleanup precondition | CLOSED | Aspect 1
D-09 | 'First-time incremental' is eliminated — it is INCREMENTAL with a seeded watermark | CLOSED | Aspect 1
D-10 | SCD1 / SCD2 are target table types, not load types. Table type + window -> eligible write strategy | CLOSED | Aspect 1
D-11 | Write strategy is a pluggable library selected by config, never by an IDMC branch. The set is settled in Aspect 3 against our own target shapes | PROPOSED | Aspect 3
D-12 | Chunk boundaries are derived at run start from declared chunk config and persisted per run, with per-chunk status, so a chunked load restarts at the failed chunk. Not static config — static boundaries go stale as data grows | PROPOSED | Aspect 2
D-13 | One taskflow invocation = one pipeline. Parallelism becomes entirely a scheduler concern | PROPOSED | Category C
D-14 | Stonebranch executes the DAG; config declares it. Dependency inside IDMC would mean editing a taskflow to add a table, which breaks the configuration-driven promise | PROPOSED | Category A
D-15 | The engine also performs a cheap defensive dependency gate — a guard, so a scheduler misconfiguration cannot silently corrupt data | PROPOSED | Category A
D-16 | New concepts go in new tables, FK'd to existing ones. Shared tables take nullable columns at most, never restructuring | CLOSED | Aspect 2
D-17 | Aurora config is the single source of truth. IDMC parameter files hold environment-scoped values only: connections, config schema, service account | PROPOSED | Aspect 2
D-18 | A load_pipeline table, one row per (table x load type), so the same table can be loaded by several load types as configuration | PROPOSED | Aspect 2
D-19 | DQ predicates are generated from config, via parameterized expression templates | PROPOSED | Category E
D-20 | One reconciliation metric definition generates both the source and the target aggregate | PROPOSED | Category E
D-21 | The watermark is a first-class writable entity, not derived from run history | PROPOSED | Aspect 2
D-22 | Parent-child is two problems: orchestration dependency is a DAG; row-level referential-integrity fallback is a data-plane concern. Different mechanisms, different tables | PROPOSED | Category A
D-23 | Config is schema-validated before it can run, including the table type x write strategy compatibility matrix | PROPOSED | Category G
D-24 | Prefer idempotent write strategies so restart and replay need no compensating cleanup. Cleanup then becomes a derivable property of (write strategy x load type) | PROPOSED | Category D
D-25 | Notifications are config-driven and severity-tiered | PROPOSED | Category F
D-26 | A target table type is the structural promise about identity and history, nothing else. Four types: SCD1, SCD2, APPEND_ONLY, SNAPSHOT. REFERENCE / STATIC collapses into SCD1 (identical invariant), and so does an accumulating-snapshot fact (structurally one row per key, overwritten in place). | AGREED | Aspect 3
D-27 | Every table type carries a TESTABLE invariant. Two payoffs: the compatibility matrix becomes derivable rather than a matter of opinion, and the invariant can be run as a generic post-load assertion for every table with no per-table code - catching a write-strategy bug on day one instead of six months later. | PROPOSED | Aspect 3
D-28 | Three table-level properties constrain write-strategy validity: has_referenced_surrogate_key, is_ri_parent, keeps_audit_lineage. TRUNCATE_INSERT is valid iff window = ALL_ROWS and the table is neither surrogate-key-referenced nor an RI parent. This replaces splitting REFERENCE from SCD1, and catches the case a split would wave through. | PROPOSED | Aspect 3
D-29 | 'Static table' is retained as a NAMED PRESET over SCD1 + those properties + FULL_REFRESH + TRUNCATE_INSERT, not as a structural table type - the same treatment as HISTORY and CATCHUP being two names over one pattern. The label costs nothing; claiming a structural difference that is not there costs a wrong validation rule. | AGREED | Aspect 3
D-30 | The table type drives the record-count balancing equation, so reconciliation becomes generic per type rather than hand-built per table. SCD1: source = inserts + updates + unchanged. SCD2: source = inserts + expiries + unchanged. APPEND_ONLY: source = inserts. | PROPOSED | Category E
D-31 | A table is classified APPEND_ONLY by one business test: on a correction, does the business write a reversing entry or update the row in place? Reversing entry means APPEND_ONLY. If the source can resend a revised version of the same event, it is NOT append-only - it is SCD1 or SCD2 keyed on the event, and mis-typing it lands corrections as duplicates that balance cleanly and go unnoticed. | PROPOSED | Category G

## open_questions
Open questions
Mirrors section 10 of requirement_and_design.md. OQ-05, OQ-06 and OQ-07 are answered by the pipeline_inventory sheet and gate the write-strategy set.
ID | Question | Blocks | Status
OQ-01 | Are there month-end snapshot tables, where every snapshot is retained rather than overwritten? | Closing Aspect 1 | OPEN
OQ-02 | How many taskflows? If the chunk loop degenerates to a single iteration when chunking is off, one taskflow suffices rather than two | Category C | OPEN
OQ-03 | Does IDMC support data-driven parallel fan-out — N parallel branches where N comes from a config query? D-13 and D-14 are chosen so the answer does not block the design | Category A | OPEN
OQ-04 | What mechanism lets a mapping task run config-generated SQL — dynamic SQL override, a generated view, or something else? | Category D | OPEN
OQ-05 | What target table types exist across the teams, and in what proportion? | Aspect 3 | OPEN
OQ-06 | Are there targets fed by more than one source table where both carry history? That case decides whether SCD2 needs a second write strategy | Aspect 3 | OPEN
OQ-07 | Is delete detection required — must the target reflect rows that disappear from the source? | Aspect 3 | OPEN
OQ-08 | Is CDC / stream acquisition ever in scope for this framework? | Scope | OPEN
OQ-09 | Can new tables be created in the shared Aurora ABC schema, or does this design need its own schema? Affects the blast-radius argument behind D-16 | Aspect 2 | OPEN
OQ-10 | Are transaction / event tables in Zone 2 scope at all - premium transactions, claim payments, commission transactions, ledger entries? ABC's build to date is entirely SCD2 plus about three static tables. If those tables stay elsewhere, cut APPEND_ONLY from the design as we cut file-based sources, record the re-entry cost, and Aspect 3 finishes with a much smaller strategy set. | Aspect 3 | OPEN